## Slide 1
Chapter 5
Variety Development Strategy and Stage Plan
Rowland Chirwa
The Business of Plant Breeding:
Market-led approaches to new variety design in Africa

## Slide 2: Chapter 5 Variety Development Strategy and Stage Plan
Rowland Chirwa
Chitedze Agricultural Research Station
P.O. Box 158, Lilongwe, Malawi

## Slide 3: Chapter 5 Objectives
Variety development strategy and stage plan:
  To enable plant breeders to construct a high quality, well-documented demand-led breeding strategy and a development stage plan, to enable good governance, rigorous decision-making and activity planning within a demand-led breeding project.
2. Stakeholder engagement: To ensure the variety development strategy and stage plan allow for involvement of stakeholders at key decision points on:
  The design, development and release of new varieties;
  Enabling new varieties to reach farmers; and
  Provide feedback on product performance and farmer adoption.

## Slide 4: Contents
New variety development strategy
Development stage plan
Timelines and critical paths
Risk management
Variety registration

## Slide 5: 1. Variety Development Strategy

## Slide 6: Variety Development Strategy
A development strategy defines the core breeding goal and creates a framework for decision-making and investment.
The strategy analyses the external environment, defines problem and answers key questions on the product being developed: ‘what’, ‘why’, ‘for whom’ and ‘how’?
The strategy has a broader scope than a development plan and considers the end product and adoption. It should precede preparing the development stage plan.

## Slide 7: Variety Development Strategy
Crop supply and demand landscape - ‘the problem’
Policy and enabling environment
Market analysis
Target clients and market segments
Variety design and market positioning
Intellectual property
Development stage and activity plan/timetable
Development costs
Development investment case
Project governance and decision-making
Client awareness and raising demand
Seed system and delivery to farmers
Monitoring post-release performance and adoption
Performance measures and risk management

## Slide 8: Group exercise – Development Strategy
What should a variety development strategy contain?
Why does each component matter in a demand-led breeding programme?
What are the benefits of creating a development strategy?

## Slide 9: 2. Development Stage Plan

## Slide 10: Development Stage Plan
A stage plan is the key tool for supporting timely decision-making and if a new genotype/line is ready for progression to the next stage and further investment.
It contains all activities needed to deliver a new variety from initial design to use by farmers.
Activities are mapped onto different stages of progression along the timeline.
Stages are directly linked and so must communicate with each other.

## Slide 11: Development Stage Plan
A Stage Plan includes the following key activities:
  Development planning
  Variety design
  Breeding, testing and evaluation
  Variety registration and scale up
  Seed production
  Monitoring and evaluation – at all stages of the variety development process

## Slide 12: Five key elements of the Stage Plan
Development planning: Brings in constructive ideas from all key stakeholders.
Variety design: Makes decisions on the type of a variety to be developed according to the criteria set by clients.
Breeding and evaluation: Identifying key resources (funds, personnel, facilities and institutions) required to determine a critical path and shortest route to delivery of the variety.
Variety registration and scale-up: Essential for plant breeders to understand the registration requirements, costs and timelines; and engage with regulatory officials from an early stage.
Seed distribution and farmer access to seed: Access to high quality, affordable seed to drive adoption and success of variety.

## Slide 13: Demand-led Breeding Stage Plan
Discovery
Early Development
Discovery
Proof of Concept
Late Development
Pre-Commercial
Commercial
Discontinue
Variety Design
A
C
D
E
F
G
H
B
Market research.
Product profile creation.
Development Investment
case created.
Identification, characterization and selection of specific traits to be used
Line Development. Development and screening of product components or pre-products rather than products
Small plot screening of products as commercial prototypes
Product prototype characterization and selection based on performance in replicated trials and wider evaluation
Preparing for launch
Product sales
Launch
Rapid Growth Peak Sales
Sales Decline
Stop sales
Elimination of inventory
Breeding & Selection
Product Evaluation and Scale-up
Life Cycle Management
Investment Decision
Initiation of research on germplasm aligned to the product concept
Commercial
Candidates
selected
requiring characterization, scaling-up and regulatory approval
Product
Launch
of specific products in specific market segments
Product discontinuation
Products that have completed discontinuation activities, and stock removed from inventories
Product concept
Key
Stage Gate decision point
Stage
Stage activities
Phase
Modified version of Syngenta Seeds stage plan
Line progression decisions

## Slide 14: Example: Developing a Small White Pea Bean Variety in Zimbabwe
Discovery
Early Development
Discovery
Proof of Concept
Late Development
Pre-Commercial
Commercial
Discontinue
Variety Design
A
C
D
E
F
G
H
B
1. Market demands baked bean
2. Product profile: small white canning bean
3. Investment case: Industry requires 360 tons/yr
Identify traits:
1. Colour – white
2. Seed size: 18 g
3. Disease resistance: < 3
4. Drought resistance
5. Canning quality: (HC > 1.7 and PWDWT > 60%)
Line Development: Identify parent lines
Generate segregating populations – these pre-products rather than products
Screen lines in small plots (nurseries and PVT) together with farmers, industry and relevant officials in variety registration
Product prototype:
Test varieties in large plots, replicated trials (IVT and AVT) and also on-farm with farmers, traders and industry and select based on set criteria
Preparing for launch:
1. Conduct DUS and VCU for variety release
2. Conduct massive demonstration plots with partners
Product sales: Launch new varieties with massive seed production, distribution promotion and sales until sales decline
Stop sales
Elimination of inventory
Breeding & Selection
Product Evaluation and Scale-up
Life Cycle Management
Investment Decision
Initiation of research on germplasm aligned to the product concept
Commercial
Candidates
selected
requiring characterization, scaling-up and regulatory approval
Product
Launch
of specific products in specific market segments
Product discontinuation
Products that have completed discontinuation activities, and stock removed from inventories
Product concept
Key
Stage Gate decision point
Stage
Stage activities
Phase
Modified version of Syngenta Seeds stage plan
Line progression decisions

## Slide 15: Benefits of Using a Stage Plan
Product adoption: Higher likelihood of varieties achieving increased farmer adoption by meeting clients’ demands
Decision-making: Enables greater focus on key milestones, generation of quality data and information required for rigorous and informed decisions
Fully integrated plan: Encourages excellent planning to seek efficiencies and a smooth flow of activities from start to completion of the new variety development
Communications: Provides a visualization framework to show progress of many lines under development within a breeding program or institution’s new variety portfolio

## Slide 16: Summary of Development Stage Plan
Essential planning process for all breeding programmes.
Contains all activities needed to deliver a new variety from initial design to use by farmers - mapped at all the different stages of progression along the timeline.
Useful not only to organise activities but also to gain inputs, support and “pull through” from clients at critical timings in the variety development process.
Important for effective communications amongst client groups and experts from different disciplines, both within each stage and across the stages.
Key tool to support timely decision-making and if a new genotype/line is ready for progression to the next stage and merits further investment.

## Slide 17: Group Discussion – Development Stage Plan
In your breeding programmes, who makes the decisions and how are the decisions made to progress germplasm - from creating crosses, through varietal release, up to final de-registering the variety from production?
At which points in the stage plan should clients, management and investors be involved in decision making?

## Slide 18: 3. Timelines and Critical Paths

## Slide 19: What is a Critical Path?
Definition: The variety development stage plan has a series of steps to design, create and deliver the new variety to farmers. The shortest possible route from design to delivery is called the “critical path”

## Slide 20: Critical Path Analysis Diagram with Risk Dependencies
New variety breeding programme
Activity
Critical path
Dependency risk
Activity 1
Activity 6
Activity 7
Activity 8
Activity 9
Activity 10
Activity 3
Activity 4
Activity 5
Activity 2
10+
9
8
7
6
5
4
3
2
1
Years

## Slide 21
Activity | TIME FRAME (YEARS) |  |  |  |  |  |  |  |  | 
 | Yr 1 | Yr 2 | Yr 3 | Yr 4 | Yr 5 | Yr 6 | Yr 7 | Yr 8 | Yr 9 | Yr 10
1. Make crosses (parent A -Sugar bean) x (parent B -drought and high Zn); (parent C - ALS ) x (parent D - BCMV and high Fe) to get F1 seeds for single and double crosses – in the greenhouse – by the breeder |  |  |  |  |  |  |  |  |  | 
2. Plant the 4-way F1 seeds in the field under controlled conditions to generate as much seed as possible at F2 generation under rainfed and generate F3s under irrigation – by the breeder |  |  |  |  |  |  |  |  |  | 
3. Plant F3s in a targeted environment for ALS and BCMV screening and select plants with desirable target traits to produce F4 seeds, and plant the F4s under irrigation to get F5 seeds – by the breeder and collaborating partners or stakeholders, depending on the traits of interest |  |  |  |  |  |  |  |  |  | 
4. Evaluate F5 lines in a single row nursery, and select best lines for grain type and yield, but also for ALS and BCMV, while increasing seed for the next season, and plant F6s to screen under drought, but also to generate F7 seeds – sample some plants from promising rows and harvest the seeds separately for mineral content analysis - by the breeder and collaborating partners or stakeholders, depending on the traits of interest |  |  |  |  |  |  |  |  |  | 
5. Evaluate selected fixed lines from drought screening in multilocation variety trials (PVT for one season, IVT for one season and AVT for two seasons) and select the best lines for yield, disease resistance and grain type – by the breeder and collaborating partners or stakeholders, depending on the traits of interest |  |  |  |  |  |  |  |  |  | 
6. Conduct on-farm trials with stakeholders to capture clients’ preferences |  |  |  |  |  |  |  |  |  | 
7. Confirm the Fe and Zn content in selected bean lines |  |  |  |  |  |  |  |  |  | 
8. Conduct Distinctiveness, Uniformity and Stability (DUS) and Value for Cultivation and Use (VCU) tests – by the designated DUS testing unit |  |  |  |  |  |  |  |  |  | 
9. Submit to Variety Release Committee (VRC) for variety release and registration – by the breeder and the variety release committee |  |  |  |  |  |  |  |  |  | 
Timeline and critical path for developing a new drought tolerant and micronutrient dense sugar bean variety with resistance to ALS and BCMV diseases in Zimbabwe

## Slide 22: Importance of Timelines and Critical Path
  Understand the timelines and associated costs to develop and register a new variety.
  Clear understanding about critical paths and approaches to risk reduction.
  Develop risk mitigation strategies.
  Understand costs and rewards associated with risks.
  Critical path analysis and pro-active risk management will help breeding team to develop new varieties that meet farmer and value chain needs in a timely and cost-effective manner.

## Slide 23: 4. Risk Management

## Slide 24: Risk Management
There are many types of hazards, incidences and problems that can occur during varietal development that can cause delays and even through to non-delivery.
In the case of planning, some scientific activities by their innovative nature may provide unexpected results.
Where the outcomes of experiments are uncertain and may require repeating, then it is advisable, if possible, to schedule them earlier in the plan and not ‘just-in time’.
Risk can also be reduced by using parallel approaches to increase the chances of a successful output, if resources permit.

## Slide 25: Risk Quantification
Identified risk | Person responsible | Impact | Likelihood | Risk reduction action
New PCR method/lab contamination | Molecular biologist | High | 20% | Industrial cleaning lab, restricted access
Field experiment off-site destroyed | Field agronomist | High | 20% | Farmer communication, signboards in field
Lost shipment of seed samples | Seed bank manager | Mod | 60% | Send in 2 lots, via specialist shipment company
Delayed recruitment of staff/specialist | Head of breeding team | High | 50% | Organize back-up contractor/more $ in budget

## Slide 26: Risk Quantification
Probability theory: Multiply —not add— individual chances of success to see the combined effect of all risks.
The combined effect of the concurrent major risks with high impact in the example below is much greater than one may think intuitively.
Combined risk effect: example -
Risk 1 High impact  60% prob. = chance of success 0.4
Risk 2 High impact  50% prob. = chance of success 0.5
Risk 3 High impact  70% prob. = chance of success 0.3
Total chance of success 0.4 x 0.5 x 0.3=0.06 or only 6%!
This may affect next decisions and course of action.

## Slide 27: Key Messages: Timelines and Risk Management
There is a need to determine optimal times to integrate requirements, tests/evaluations and data generation for demand-led parameters
Timescales must be clearly defined
Find creative ways to not extend and preferably shorten timescales whilst including demand-led components
Use critical path analysis and risk mitigation
Use data to make decisions

## Slide 28: Group Exercise: Timelines and Critical Paths
What are the biggest risks in your breeding programme?
How do you mitigate against these risks?

## Slide 29: 5. Variety Registration

## Slide 30: 4. Variety Registration
Current knowledge of registration system and release requirements is essential, at national and regional levels.
Timelines and costs.
Can one help to speed up the registration process by engaging with the regulatory officials?

## Slide 31: Demand-led Variety Registration
Consumer traits and regulatory hurdles.
Demand-led breeding is complex and can take longer - so a smooth registration process is a key factor.
Regional harmonization may influence market size and subsequent investment decisions.
  Demand-led variety registration may be influenced by international regulations such as UPOV, breeders’ rights and national registration agencies.

## Slide 32: Demand-led Variety Registration
In each country, National Variety Registration Committee (NVRC ) makes a decision to release or reject a new variety, based on data compiled in the release proposal
Some countries charge a fee, others do not, for tests
Ideally, release is based on merit/uniqueness of variety
Uniqueness of a variety that addresses demand-led traits should be considered sufficient to distinguish a new variety from others and give it merit for release

## Slide 33: Demand-led Variety Registration
Some countries require yield improvement vs benchmark
Thus the need for yield gain vs consumer demand-led traits issues need to be clarified at the variety design stage
The fact that each country has its own Seed Act makes it costly for seed companies to release and market new varieties in different countries in sub-Saharan Africa
One way to reduce registration costs is to harmonize variety registration regulations across countries, in regional sub groupings (e.g. SADC and COMESA countries)

## Slide 34
Chapter 5
Variety Development Strategy and Stage Plan
Rowland Chirwa
The Business of Plant Breeding:
Market-led approaches to new variety design in Africa